## Web Development
Social Influencer Web App Requirements - For Influencer and Advertisers

Sl No	Reqirements	Team member	Status
1	Firebase Authentication for Login		Completed(email, password)
2	Storing data and retriving data in the firebase Database
3	Hosting the NodeJS application to the Firebase Server		Completed
Influencers

1	Login in the web app (Firebase Authentication)
1.1	Google Login	Ankitha H	Planned
1.2	Register in the Web application	Thrinath Sirna	In-progress
1.3	Forgot password	Thrinath Sirna	Planned
1.4	UI design for both login and registration.	Chethan G C	In-Progress
2	Social media profile creation			Wireframes needs to be done
2.1	Details of the Influncer	Chethan G C
2.2	Social media links of Instagram, Facebook and YouTube.	Sudarshana SS	Need clarity
3	Campaign activities for promotions.			Wireframes needs to be done
3.1	Dashboard for the Influncer to see the details of campaigns.	Ankitha H		Doubts to be clarified
3.2	Listing the running promotion campaigns.	Sudarshana SS
3.3	Listing the past promotion campaigns that he was part-of. (only for that Influencer)	Girish KV
3.4	Provision for selecting and applying for a promo.	Girish KV
Advertisers

1	Login in the web app			Wireframes needs to be done
1.1	Google Login	Thrinath Sirna	Planned
1.2	Register in the web app	Thrinath Sirna	In-Progress
1.3	Forgot password	Ankitha H	Planned
1.4	UI design for both login and registration	Ankitha H	In-Progress
2	Create the promotion campaigns for the web app
2.1	Name of the product, Description of the product, Image of the product, Pricing for the product promotion campaign, Start and end date of the campaign.	Girish K V, Ankitha H	planned
3	Filter and search influencers
3.1	Global search	Chethan G C
3.2	Search based on the broad categories.	Chethan G C, Sudarshana SS
4	Send Promo Request to influencers	Girish K V
5	Dashboard to see all the running promotion campaigns (Past and Running).	Sudarshana SS

## Software and Hardware Requireme
Software and Technology Requirements
SLNO	Software/Technology Requirements
1	Firebase Authentications
2	Firebase Real time Database
3	Firebase Hosting
4	Functions in Firebase
5	VS code for web.
6	Android Studio
7	Wireframe ( Online tools or Adobe XD or Photoshop) for the web and android.
8	Node JS 8.
9	Express.
10	Firebase Tools.
11	Postman.
12	Javascript.
13	CSS 3.
14	HTML 5.
15	JAVA.
16	XML.

Hardware Requirements
SLNO	Hardware Requirements
1	Android Mobile
2	Laptop/Desktop with Windows 10. RAM – 8 GB min (16 GB recommended)

## Android
Social Influencer Mobile App Requirements - For Influencer and Advertisers

Sl No	Reqirements	Team member	Status
Influencer

1	Login in the mobile app
1.1	Google Login for mobile app	Ankitha H	In-progress
1.2	Register in the mobile application	Thrinath Sirna	In-progress
1.3	Forgot password	Thrinath Sirna	Planned
1.4	UI design for both login and registration.	Chethan G C	Completed
2	Social media profile creation
2.1	Details of the Influncer	Chethan G C
2.2	Social media links of Instagram, Facebook and YouTube.	Sudarshana SS
3	Campaign activities for promotions.
3.1	Dashboard for the Influncer to see the details of campaigns.	Ankitha H	Planning
3.2	Listing the running promotion campaigns.	Sudarshana SS
3.3	Listing the past promotion campaigns that he was part-of. (only for that Influencer)	Girish KV
3.4	Provision for selecting and applying for a promo.	Girish KV

Wireframes
Login and Register wireframes for android app		Click here to check